## Sheet1
Project Logbook
Week | Date | Options/Evaluations/Decisions | More details | Issues | Lessons Learned
1 | 9/1-9/6 | Came up with project ideas
2 | 9/7-9/13 | Picked Project Groups and Project Idea: Smart Plant Monitor Created a Block Diagram and Project Definition Template
3 | 9/14-9/20 | Brainstormed Parts for Project | UC: Arduino Uno Sensors: DHT11, Photoresistor, Soil Sensor Output: RGB LED Picked these components since we have all used them (other than the Soil Sensor), they are easy to code and they are reliable | Need to figure out which soil sensor to use and a way for users to input plants data. | Reading Data sheets are important to figure out which components will best suit the project
4 | 9/21-9/27 | Picked a the Capacitive Soil Moisture Sensor | Picked the Capacitive Soil Sensor since it is more durable and reliable
5 | 9/28-10/4 | Make test codes for each component | Found the libraries and data sheet for each component that are currently being used. The test codes for each component worked, based on the test codes. | Some of the aspects for the test codes will be implemented into the code, other aspects need to be altered in order to carry out what the Smart Plant Monitor is supposed to do | Test codes are very important to figure out which components work before implementing into the project. If there is an issue with the component, it will be easy to troubleshoot since the component is isolated.
6 | 10/5-10/11 | Start Coding the project to make a proof of concept midterm, create the presentation | Soil Sensor, Photoresistor and Temperature Sensor are all working | Instead of orange LED for not enough sunlight, it will be purple since orange did not look good, too similar to yellow. Need a way to to not make the light sensor go off at night | Getting an orange color in an RGB LED is challenging. Came across an issue with the the light sensor and what happens when it is nighttime. Having the light sensor detect that it is night will save some of the battery of the Smart Plant Monitor.
7 | 10/12-10/18 | Make changes to the presentation and review it before the proof of concept presentation midterm
8 | 10/19-10/25 | Added the nighttime clock. Attempted to add IR sensor with remote | Nighttime clock allows users to define how long night is and what light level. | Length of night is built into the code, users can not set how long night is. Night level is used to reset the sunlight intake daily. Could not get IR sensor to work, opted to try different components | Figuring out how to create a "Nighttime clock" was challenging. After research and time constraints, it was better to hardcode a nighttime mode
9 | 10/26-11/1 | Added Key Membrane and switched to Arduino Mega | Switched to Arduino Mega to add the key membrane for more pins Users enter optimal values using the key membrane |  | Sometimes not all components work. The IR sensor + remote was not working properly, it was easy to determine this issue due to testing the component with the test code. After a few weeks of failures, the decision was made to switch components
10 | 11/2-11/8 | Added Push Button | Users can reset system holding down for about 5 seconds | Could not get a reset button to work on key membrane, mostly due to coding problems, added a separate component for the reset aspect | Steep learning curve with coding. If our knowledge with C++ was a little better then there should have been no issue with getting the reset button to work on the key membrane
11 | 11/9-11/15 | Added LCD Users can input how frequent the sensors monitor | LCD helps users see what values they are inputting |  | The display will help users see what they inputted, just in case they it the wrong numbers. This was helpful when testing
12 | 11/16-11/22 | Work on updating schematic, report documents
13 | 11/23-11/29 | Work on Updating PCB Layout
14 | 11/30-12/6 | Work on Updating PCB Layout, updating report documents, design files
15 | 12/7-12/13 | Created a Power Budget, worked on report documents, fixed the schematic, created the final project presentation | Switched the 9V battery with a USB battery pack so that the run time for the smart plant monitor can last a week | Created a Power Budget and realized that the 9V battery would only last 1-2 hours | Power Budget showed the flaws with the 9V battery. The design was made to switch to a battery bank for more runtime
16 | 12/14-12/19 | Finishing touches on Final Project Presentation | Practiced presentation | Timing conflicts with finals and work | Working on a group project all semester heavily relies on communication and dedication.